## Test Plan
Test Plan (in progress)
1. Test Plan ID: 1
2. Purpose The project under test (https://ostrov-shop.by/) is a stably functioning web resource that allows Internet users to purchase various goods and related services (delivery). The main purpose of testing the "Search element on the web page" (hereinafter - "Search element") is the thorough verification of all the features in different OS (Windows 10, Windows 7) and browsers (Chrome, Firefox). About 80% of the testing schedule will be spent on testing negative scenarios and critical situations, which can also reveal critical errors.
3. Features To Be Tested We should cover User Requirements (UR-*), Business Rules (BR-1, BR-2, BR-3, BR-5), Quality Attributes (QA-1), Limitations (L-1, L-3) and Detailed Specifications (DS-*) with Smoke tests and Critical path tests.
4. Features Not To Be Tested BR-4: no implementation required. QA-2, QA-3: no implementation required. L2, L4: no implementation required.
5. Test strategy and approach As a result of the first testing cycle, where the functional tests take place, there will be some corrections and additions introduced into the Test Plan. The client will be given all daily reports about the testing process, bugs found, propositions about the improvements should be made. All the defects found will be added to the bug tracker for further fix and verification. Testing will be carried out both by hand and automatically (smoke tests) using unit tests (White Box Testing). There are planned five stages of testing: 1) Requirements analysis, Test Plan creation, partial fulfillment of some functional tests (smoke tests). 2) Detailed fulfillment of functional tests uncovering and describing the bugs. 3) Cross Browser and Cross Platform testing with uncovering and describing the bugs. 4) Fixed bugs verification and Regression testing fulfillment. 5) UI testing with uncovering and describing the bugs. Such kind of testing system allows us to carry out a detailed testing and prevent and/or fix bugs on early stages, which will save the end use time and money.
6. Criteria • Acceptance criteria: 100% success of test cases on smoke test level and 90% success of test cases on critical path test level (see “Test cases success percentage” metric) if 100% of critical and major bugs are fixed (see “Overall defects fixed percentage” metric). Final requirements coverage by tests (see “Requirements coverage by tests” metric) should be at least 80%. • Entry criteria: new build. • Testing suspension criteria: critical path test must begin only after 100% success of test cases on the smoke test (see “Test cases success percentage”); test process may be suspended with at least 25% test-cases executed with at least 50% failure rate (see “Stop-factor” metric). • Testing resumption criteria: more than 50% of bugs found during the previous iteration are fixed (see “Ongoing defects fixed percentage” metric). • Exit criteria: more than 80% planned for the current iteration test cases are executed (see “Test-cases execution percentage”).
7. Test Environment OS: 1. Windows 10, Windows 7; Browser: Chrome, Firefox, Edge; СI: Jenkins CD: Docker
8. Test deliverables Test Plan > Check list > Test Cases > Bug Reports > Test Summary Report
9. Resources • Software: 6 virtual machines. • Hardware: 3 standard workstations (RAM, CPU model and clock speed - TBD). • Personnel: One fullstack developer with testing experience (100% workload during the project). Roles: team lead, senior developer. One frontend developer with testing experience (100% workload during the project). Role: middle developer. One manual tester with JS knowledge (100% workload during the project). Role: junior tester. • Time: 15 days (120 work hours). • Finances: according to the approved budget.
10. Schedule • 15.02 - 16.02 – requirements testing and finalizing. • 17.08 - 15.08 – test-cases and scripts for automated testing creation. • 16.02 - 18.02 – main testing stage (test-cases execution, bug reports creation). • 19.02 - 01.03 – testing finalization, reporting. • 02.03 – extra day for unplanned testing activities.
11. Roles and responsibilities • Senior developer: participation in requirements testing and code review. • Middle developer: participation in requirements testing and code review • Tester: requirements testing, test plan creation, test-cases creation, test-cases execution, bug reports creation, test summary report creation.
12. Risk evaluation • Personnel (low probability): if any team member is out of office, we can contact the representatives of the PTUE “ZapadChimTorg” to get a temporary replacement. • Time (high probability): the customer has indicated a deadline as of 26.02, therefore time is a critical resource. It is recommended to do our best to complete the project by 01.03 so that one extra day (02.03) remains available for any unexpected issues. • Other risks on the project (high probability): changing requirements.
13. Approvals

## Test Case
ID No. | Headline | Environment | Pre-condition | Steps | Data | Expected result | Post-condition | Status (pass/fail)
1 | Login to the user's personal account | OS: Windows 10, version 1607 (64-bit) Browser: Google Chrome Version 88.0.4324.146 (Official Build) (64-bit) | To be located on the main page and be a registered user of the online store: https://ostrov-shop.by/ | 1. Click "Login" tab 2. Enter valid data to the "Email" field (required) 3. Enter valid data to the "Password" field (required) 4. Click "Login" button | Valid values: Email: test-01@gmail.com Password: ostrovshop123 | 1. "Login to a personal account" dialogue should open 2. The entered email should be displayed in the "Email" field 3. The characters in a password field should be masked with circles according to the quantity of the entered characters. 4. The user should successfully login to the personal account

## Bug Report
ID No. | Summary | Description | Attachment | Severity | Priority | Reproducibility | Environment
1 | The list of product categories is not displayed when hovering a cursor over the "Stationery" section while in the "Catalogue" menu | Steps to reproduce: 1. Go to https://ostrov-shop.by/ 2. Hover a cursor over the "Stationery" section 3. Pay attention to the behaviour on the page (see attachment 1) Actual result: Slider with ads is displayed next to the "Stationery" section. Expected result: The list of product categories should be displayed next to the "Stationery" section (see attachment 2). | 1. https://prnt.sc/yv63hg 2. https://prnt.sc/yvvr6f | trivial | low | always | OS: Windows 10, version 1607 (64-bit) Browser: Google Chrome Version 88.0.4324.146 (Official Build) (64-bit)